Proposed Timeline (Schedule)

12/31/04  	Have a 2004 Nonpoint Source Management Program Update submitted to EPA for its approval

10/04       	Meeting of the NPS Liaison Workgroup that provides final comments on the 2004 Update

8/15/04    	Deadline for NPS category workgroups to have their draft sections prepared for  distribution to the full NPS Liaison Workgroup for review and action at the 10/04 meeting

July/August 	Individual NPS category workgroups work on refining

goals/objectives/milestones of their respective categories

6/04          		Meeting of the NPS Liaison Workgroup.  This meeting will include discussion of the first full draft of the 2004 Update

4/1/04    		Deadline for NPS category workgroups to have a draft of their

goals/objectives/milestones to DEP

January-April 	NPS category workgroups work independently to meet/discuss and draft

goals/objectives/milestones