## Sheet1
Funding Breakdown
Project Number | Title/Operator | County | Township | Completion Date (Anticipated) | Date Awarded | Anticipated Bid Opening Date | Project Acreage | Project Cost or Estimate | Title IV | 10% Set Aside | Title IV - ACSI | Title IV - Anthracite Area | Title IV - Metals Recovery | Collected Bond | Bond Forfeiture & Other Programs | Growing Greener
Projects Completed during Calendar Year 2005
AD 0754 | LARKSVILLE SOUTHWEST | Luzerne |  | 2005-06-21 | 2004-12-08 |  | 0 | 69297.92 | 69297.92
AD 0766 | DMF 014-101.1 | Schuylkill | Tremont | 2005-09-30 | 2005-09-30 |  | 0 | 6228.77 | 6228.77
AMD 03(0743)102.1 | NUMINE (WHITE LAKE) | Armstrong | Cowanshannock | 2005-06-03 | 2005-02-11 |  | 2.8 | 31488 |  |  | 31488
AMD 14(6816)101.1 | PINE GLEN EAST | Centre | Burnside | 2005-09-30 | 2004-05-06 |  | 0 | 873011.15 |  | 714948.35 |  |  |  | 158062.8
AMD 26(0429)103.1 | MELCROFT (GA) | Fayette | Saltlick | 2005-11-28 | 2004-06-30 |  | 0 | 325000 |  |  | 325000
AMD 56(3077)202.1 | HOFFMAN ZION CHURCH (HOFFMAN RUN) | Somerset | Jenner | 2005-11-22 | 2004-09-14 |  | 0 | 435540.48 | 435540.48
BF 091-101.1 | GLOSEK BROTHERS COAL CO. | Northumberland | West Cameron | 2005-05-10 | 2004-05-07 |  | 33.9 | 393782.12 | [5 empty] | 5000 |  | 388782.12
BF 302-105.1 | REM COAL CO. | Jefferson | Union | 2005-10-31 | 2003-04-08 |  | 2 | 233986.49 | [5 empty] | 233986.49
BF 372-101.1 | GLENN COAL CO. (ACT 181) | Jefferson | McCalmont | 2005-05-27 | 2003-10-22 |  | 48.8 | 290998 | 246797 |  |  |  |  | 44201
BF 442-101.1 | T & T CLAY COMPANY | Clearfield | Boggs | 2005-09-21 | 2005-04-28 |  | 12 | 97908.72 | [5 empty] | 21220.09 | 76688.63
BF 467-101.1 | PENGROVE COAL COMPANY(BEAN) | Butler | Cherry Valley | 2005-07-07 | 2004-10-05 |  | 2 | 106608.95 | [5 empty] | 106608.95
BF 488-101.1 | McGAL COAL | Allegheny | Forward | 2005-05-06 | 2004-10-05 |  | 4 | 114010.6 | 110572.6 |  |  |  |  | 3438
BF 511-101.1 | LAURA D COAL, INC. | Somerset | Jenner | 2005-07-29 | 2004-10-26 |  | 4.3 | 23600 | [5 empty] | 22320 | 1280
CRF 006-101.1 | WHITE ROCK FUEL CO. | Fayette | Georges | 2005-01-19 | 2003-12-09 |  | 22 | 78435.42 | [5 empty] | 21758.52 | 56676.9
DMF 010-102.1 | LV COAL AND SKY HIGH COAL COMPANY | Schuylkill | Porter | 2005-11-03 | 2005-06-07 |  | 1 | 53423 | [5 empty] | 3230 | 50193
OSM 02(1496)101.1 | WEST STARZ WATERLINE (PASS THRU) | Allegheny | West Deer | 2005-06-09 | 2004-07-01 |  | 0 | 28945.17 | 28945.17
OSM 04(1261)101.1 | FREEDOM | Beaver | New Sewickley | 2005-09-01 | 2005-05-24 |  | 1 | 58438.35 | 58438.35
OSM 10(6375)101.1 | DEEGAN WEST | Butler | Marion | 2005-05-09 | 2003-12-18 |  | 18.1 | 190270.1 | 190270.1
OSM 11(BARNES-WATKINS)102.1 | BARNES-WATKINS REF. PILE REMED.(SW 30438 | Cambria | Barr | 2005-05-31 | 2004-03-12 |  | 4.5 | 1214872.5 | 1124872.5 | [6 empty] | 90000
OSM 14(4556)101.1 | CASANOVA | Centre | Rush | 2005-04-25 | 2004-02-05 |  | 8.1 | 43943.2 | 43943.2
OSM 17(4454)101.1 | BCI WATERLINE (GA) | Clearfield | Beccaria | 2005-05-24 | 2005-04-01 |  | 0 | 31918.87 | 31918.87
OSM 17(6955)101.1 | BARK CAMP COMPLEX (GA) | Clearfield | Huston | 2005-02-18 | 2005-01-18 |  | 0 | 333333 | [7 empty] | 333333
OSM 17(7163)102.1 | McDOWELL MOUNTAIN SOUTH | Clearfield | Bradford | 2005-09-14 | 2005-07-12 |  | 0 | 189786 | 189786
OSM 19(4034,2000,1688) | CENTRALIA MERCURY MONITORING | Columbia | Centralia | 2005-04-14 | 2004-12-01 |  | 0 | 112260 | 112260
OSM 24(2211)102.1 | RIDGWAY HILL | Elk | Ridgway | 2005-05-20 | 2004-09-30 |  | 7 | 122449 | 141829.74
OSM 26(0151)202.1 | DUNBAR TWP. | Fayette | Dunbar | 2005-10-06 | 2004-09-03 |  | 3 | 79278.84 | 79278.84
OSM 30(2766)101.1 | CRUCIBLE NORTH | Greene | Cumberland | 2005-04-26 | 2004-05-28 |  | 8 | 216057.62 | 201057.62 | [5 empty] | 15000
OSM 32(2444)101.1 | CALVERY CHURCH | Indiana | Green | 2005-07-01 | 2005-03-07 |  | 5.4 | 45308.93 | 45308.93
OSM 35(2090)101.1 | JESSUP CEMETERIES | Lackawanna | Jessup | 2005-01-12 | 2002-06-20 |  | 70.3 | 1504773.36 | 12740.5 |  |  | 1492032.86
OSM 37(0185)101.1 | FRIDAYS HILL ROAD | Lawrence | Wayne | 2005-05-19 | 2004-03-04 |  | 10 | 64007.5 | 64007.5
OSM 37(S.WELLS McCREADY)101.1 | S. WELLS McCREADY (NW 30569) - PHASE III | Lawrence | New Beaver | 2005-12-06 | 2004-01-29 |  | 14.5 | 153021.88 | 145021.88 | [6 empty] | 8000
OSM 40(2128)101.1 | WARRIOR GAP | Luzerne | Warrior Run | 2005-06-06 | 2004-09-27 |  | 19.9 | 240887.25 | 240887.25
OSM 40(2239,3035)101.1 | NEW BOSTON ROAD 2 NORTH, OLD BOSTON | Luzerne | Jenkins | 2005-11-16 | 2005-06-06 |  | 35 | 364777.79 | 364777.79
OSM 49(2067)101.1 | GOWEN CITY NORTHWEST | Northumberland | Coal | 2005-05-24 | 2004-03-05 |  | 20.1 | 271638.87 | 271638.87
OSM 54(3634)102.1 | MOUNT PLEASANT SOUTH | Schuylkill | Foster | 2005-08-18 | 2004-03-24 |  | 48.4 | 524423.4 | 524423.4
OSM 54(TREMONT II)101.1 | TREMONT II - CONSTRUCTION (NE 30437) | Schuylkill | Tremont | 2005-09-30 | 2004-03-04 |  | 0 | 174309.62 | 158309.62 | [6 empty] | 16000
OSM 56(0240)101.1 | CENTRAL CITY | Somerset | Shade | 2005-01-05 | 2004-09-03 |  | 0.1 | 120983 | 120983
OSM 56(0775)102.1 | LISTIE SOUTH | Somerset | Somerset | 2005-05-19 | 2004-03-24 |  | 14 | 250110 | 250110
OSM 63(1441)101.1 | MCDONALD SOUTH | Washington | McDonald | 2005-06-15 | 2005-04-18 |  | 6 | 402502.75 | 402502.75
OSM 63(3803)201.1 | MONONGAHELA SOUTH NO. 1 (CONSULT.DESIGN) | Washington | Monongahela | 2005-07-14 | 2003-10-07 |  | 0 | 1474083.7 | 1474083.7
2005 Completions: |  | 40 | Projects |  |  |  | 426.2 | 11345700.32 | 7145832.35 | 714948.35 | 356488 | 1492032.86 | 0 | 619825.85 | 199838.53 | 836115.12
Projects Completed Year-to-date, Calendar Year 2006
OSM 13,40(4966,4121)101.1 | BUCK MOUNTAIN & OWL HOLE | Carbon | Lausanne | 2006-01-26 | 2005-10-12 |  | 0.2 | 24916 | 24916
2006 Completions: |  | 1 | Projects |  |  |  | 0.2 | 24916 | 24916 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Active Projects, Under Construction, Future Completion Date
AMD 02(0488)102.1 | WINGFIELD PINES (GD050201) | Allegheny | Bridgeville | 2007-12-31 | 2005-11-17 |  | 0 | 650955 |  |  | 650954 |  |  |  |  | 1
AMD 08(3998)101.2 | COAL RUN AMD REMEDIATION (GA) | Bradford | Franklin | 2006-12-31 | 2005-04-20 |  | 0 | 23270 |  |  | 23270
AMD 10(6594)101.1 | DESALE NORTH AMD ABATEMENT PROJECT | Butler | Venango |  | 2004-11-02 |  | 65 | 123357 |  |  | 123357
AMD 11(2707)101.2 | JOHNSTOWN REDEVELOPMENT (GA) CD040137 | Cambria | Stonycreek | 2006-12-31 | 2005-04-01 |  | 0 | 37114 |  |  | 37114
AMD 11(2711)102.1 | JANDY (CD050369) | Cambria | Richland | 2007-06-30 | 2005-11-17 |  | 0 | 51511 |  | 51510 | [5 empty] | 1
AMD 11(4090)101.1 | DUMAN LAKE PARK (BARNES AND TUCKER) (GA) | Cambria | Blacklick |  | 2004-09-17 |  | 0 | 970120.98 | 970120.98
AMD 16(1061)101.1 | LC20D PASSIVE MINE DRAINAGE (GA) | Clarion | Farmington | 2006-12-31 | 2005-03-23 |  | 10 | 351734 |  |  | 351734
AMD 24(6134)103.1 | BRANDY CAMP (KD050010) | Elk | Fox | 2006-12-31 | 2005-11-17 |  | 0 | 452999 |  | 452998 | [5 empty] | 1
AMD 26(2767)102.1 | ROMNEY NORTH (KALP DISCHARGE)(GA) | Fayette | Saltlick | 2006-12-31 | 2005-04-20 |  | 10 | 1661407 |  | 1661407
AMD 26(2767)103.1 | ROMNEY NORTH (KALP DISCHARGE)(GA) | Fayette | Saltlick |  | 2005-04-20 |  | 10 | 150000 |  |  | 150000
AMD 31(6959)102.1 | JOLLER (CD050205) | Huntingdon | Todd | 2006-12-31 | 2005-11-17 |  | 0 | 32571 |  | 32570 | [5 empty] | 1
AMD 32(2404)101.1 | TIDE MINE POOL TREATMENT (GA) | Indiana | Center | 2005-05-01 | 2004-05-13 |  | 50 | 394773.5 |  |  | 394773.5
AMD 32(2404)102.1 | JUDY 14 TREATMENT SYSTEM REHAB. - YC2C | Indiana | Center | 2006-12-31 | 2005-11-17 |  | 0 | 93562 |  |  | 93561 |  |  |  |  | 1
AMD 33(1147)101.1 | SUGAR CAMP RUN DISCHARGES (KD050285) | Jefferson | Winslow | 2007-12-31 | 2005-11-17 |  | 0 | 82555 |  |  | 82554 |  |  |  |  | 1
AMD 42(0421)101.1 | TWO MILE RUN (PASS THROUGH AGREEMENT) | McKean | Sergeant | 2005-12-31 | 2003-09-18 |  | 5 | 53575 |  |  | 53575
AMD 56(1488)102.1 | JENNER PASSIVE TREATMENT SYSTEM (GA)CD040227 | Somerset | Jenner | 2006-12-31 | 2005-05-03 |  | 0 | 106682 |  |  | 106682
AMD 56,65(RES.RECOVERY 3)103.1 | METRO PHASE 3 | Somerset | Elk Lick | 2005-10-31 | 2003-09-26 |  | 0 | 500000 |  |  |  |  | 500000
AMD 59(1891,6657)101.1 | ARNOT SAP-ALD (GA) | Tioga | Bloss | 2006-12-31 | 2004-11-04 |  | 0 | 102603 | [7 empty] | 102603
BF 378-101.1 | HILL COAL CO. ENTERPRISES (I) (ACT 181) | Clearfield | Boggs | 2007-02-12 | 2005-02-15 |  | 37 | 425310 | 390310 |  |  |  |  | 35000
BF 438-102.1 | AVERY COAL CO., INC. | Clinton | Beech Creek | 2005-10-31 | 2003-05-19 |  | 12 | 1575121.73 | [5 empty] | 278435.79 | 226599.73 | 1070086.21
BF 440-201.1 | ATTILIO CICCONI | Fayette | Luzerne | 2006-07-11 | 2004-11-08 |  | 54 | 992000 | [5 empty] | 36000 | 204400.03 | 751599.97
BF 469-201.1 | ROBERT F. TAYLOR & BRYAN NORTHWEST | Armstrong | Wayne | 2007-01-11 | 2005-06-29 |  | 79 | 992023 | 674575.64 |  |  |  |  | 150590 | 166857.36
BF 472-101.1 | CT & LT ENTERPRISES, INC. | Greene | Jefferson | 2005-07-23 | 2003-07-31 |  | 23.8 | 130155 | [5 empty] | 77851.25 | 52303.75
BF 485-101.1 | ELIZABETHVILLE NORTH (AD COAL COMPANY) | Dauphin | Washington | 2005-09-07 | 2004-09-15 |  | 4.5 | 184510 | 104241 |  |  |  |  | 1869.6 | 78399.4
BF 490-101.1 | GRAHAM BROS. LUMBER CO., INC. | Clearfield | Boggs | 2006-05-31 | 2004-01-22 |  | 0 | 421578.4 | [5 empty] | 188818.47 | 232759.93
BF 493-101.1 | THOMPSON BROTHERS COAL CO. | Clearfield | Morris | 2006-01-20 | 2005-05-12 |  | 54.5 | 293375.5 | [5 empty] | 293375.5
BF 499-101.1 (ACT 181) | H & D COAL COMPANY(H&D #8) | Butler | Marion |  | 2006-01-26 |  | 7 | 111800.01 | [5 empty] | 111800.01
BF 504-101.1 | ROYAL RECLAMATION, INC. | Westmoreland | Mount Pleasant | 2005-10-27 | 2005-04-06 |  | 8.2 | 45401.67 | [5 empty] | 2175 | 43226.67
BF 505-101.1 | CHARLES BIZICH | Westmoreland | Bell |  | 2004-12-01 |  | 4 | 32050 | [5 empty] | 4008.07
DMF 011-101.1 | MEADOWS AND LEONARD MINING, INC. | Cambria | Adams | 2007-03-05 | 2004-03-08 |  | 19.5 | 186983 | [5 empty] | 186983
OSM 02(0350,0351)101.1 | IMPERIAL NORTH/CLINTON SOUTHEAST | Allegheny | Findlay |  | 2005-11-30 |  | 0 | 1188000 | 1188000
OSM 02(0796)101.1 | WEST SMITHFIELD ROAD | Allegheny | Lincoln | 2006-05-15 | 2004-10-14 |  | 16 | 223621.5 | 223621.5
OSM 02(3813)101.1 | RED HOT / CHRISTY ROAD | Allegheny | West Deer |  | 2005-10-12 |  | 0 | 34225 | 34225
OSM 02(4422)102.1 | FISHING RUN (GD050121) | Allegheny | South Fayette | 2007-06-30 | 2005-11-17 |  | 0 | 329249 | 329248 | [6 empty] | 1
OSM 03(3902)101.1 | CRAIGSVILLE SOUTHWEST | Armstrong | West Franklin | 2006-05-02 | 2005-03-04 |  | 54.8 | 919328.7 | 919328.7
OSM 04(0153)101.1 | JORDAN RUN | Beaver | Big Beaver | 2006-04-05 | 2005-07-01 |  | 24 | 367419 | 367419
OSM 04(1259)101.1 | FALLSTON | Beaver | Fallston |  | 2005-10-05 |  | 2 | 58900 | 58900
OSM 10(3760)103.1 | ANNANDALE S.W. III | Butler | Cherry |  | 2005-10-20 |  | 84.1 | 1489767 | 1489767
OSM 10(4506)101.1 | WEST LIBERTY SOUTH WEST | Butler | West Liberty | 2006-06-14 | 2005-07-19 |  | 18 | 288328 | 288328
OSM 11(0826)102.1 | SPANGLER ATHLETIC FIELD | Cambria | Northern Cambria |  | 2005-11-15 |  | 2 | 131631.4 | 131631.4
OSM 11(1018)101.1 | HOLLENTOWN NORTHEAST | Cambria | Reade | 2006-05-02 | 2005-03-04 |  | 39.6 | 548319 | 548319
OSM 11(BARNES-WATKINS)103.1 | BARNES-WATKINS PHASE2 (GA) CB040457 | Cambria | Barr | 2006-12-31 | 2005-04-11 |  | 13.5 | 3188958 | 3188958
OSM 13(3216)101.1 | SPRING MOUNTAIN | Carbon | Packer |  | 2006-02-10 |  | 13.5 | 306281.8 | 306281.8
OSM 13(4066)102.1 | LANSFORD NORTH 2 | Carbon | Lansford | 2006-03-05 | 2003-10-23 |  | 105 | 2459044.45 | 2196715.9 |  |  | 262328.55
OSM 13(4652)101.1 | LANSFORD EAST | Carbon | Lansford | 2005-12-20 | 2004-12-23 |  | 11.5 | 282284 | 282284
OSM 14(6818)101.1 | PINE GLEN SOUTHEAST | Centre | Burnside |  | 2006-02-07 |  | 0 | 117767 | 117767
OSM 16(0065)101.1 | FAIRHILL COAL | Clarion | Redbank |  | 2005-11-08 |  | 10.25 | 106142 | 106142
OSM 16(6045)101.1 | FROGTOWN NORTHEAST (LIMESTONE TOWNSHIP WATERLINE (GA) | Clarion | Limestone | 2007-12-31 | 2005-07-07 |  | 0 | 1134064 | 1134064
OSM 17(0084)103.1 | NEEDFUL WEST | Clearfield | Bradford | 2006-02-03 | 2005-06-23 |  | 0 | 359900 | 359900
OSM 17(7103)101.1 | OHIO SCHOOL (CONSULT. DESIGN) | Clearfield | Decatur | 2005-06-15 | 2004-04-28 |  | 74 | 373471.3 | 373471.3
OSM 17(7158)101.1 | SHAWVILLE NORTH | Clearfield | Goshen | 2006-06-22 | 2005-06-23 |  | 33 | 681767 | 681767
OSM 17(7163)101.1 | McDOWELL MOUNTAIN SOUTH | Clearfield | Bradford |  | 2005-12-28 |  | 58 | 797419 | 797419
OSM 24(3894)101.1 | WINSLOW HILL II | Elk | Benezette | 2006-05-15 | 2005-01-28 |  | 14.5 | 565635.56 | 565635.56
OSM 24(BRANDY CAMP)101.1 | BRANDY CAMP/BLUE VALLEY (NW 30032) | Elk | Horton | 2006-06-30 | 2004-01-08 |  | 2 | 200000 |  |  | 182000 |  |  |  |  | 18000
OSM 24(DENTS RUN)101.1 | DENTS RUN-WINSLOW HILL 3 (CORPS OF ENG.) | Elk | Benezette | 2008-06-30 | 2004-12-03 |  | 0 | 3028000 | 1473617.88 |  | 1344382.12 |  |  |  |  | 210000
OSM 26(2718)103.1 | PERCY MINE FIRE | Fayette | North Union | 2007-06-22 | 2005-04-21 |  | 200 | 3203000 | 3203000
OSM 26(4733)101.1 | GANS NORTHWEST | Fayette | Springhill | 2006-05-15 | 2005-02-15 |  | 12.2 | 88612.1 | 88353.75
OSM 30(2791-MATHER)101.1 | MATHER PILE RECLAMATION (SW 30649) | Greene | Morgan | 2005-12-31 | 2004-04-28 |  | 77 | 2971394 | 2832394 | [6 empty] | 139000
OSM 31(6026)101.1 | LUCIANA BOTTOMS WEST | Huntingdon | Todd | 2006-02-10 | 2004-05-28 |  | 90 | 1284767 | 1284767
OSM 32(2425)102.1 | LAUREL RUN PHASE 2 (GA) | Indiana | Brush Valley | 2006-09-30 | 2005-05-09 |  | 8 | 287012.5 |  |  | 287012.5
OSM 32(2722)101.1 | WEHRUM NORTHEAST | Indiana | Buffington | 2006-12-31 | 2005-06-10 |  | 0 | 46180 | 46180
OSM 32(3327)101.1 | GLEN CAMPBELL NORTH | Indiana | Banks | 2006-05-15 | 2004-12-29 |  | 20 | 256182.4 | 256182.4
OSM 35(1519,2087,2088)201.1 | FALL RUN, S.W. & CARBONDALE N.E. | Lackawanna | Carbondale | 2008-05-08 | 2005-09-06 |  | 226 | 5413233 | 5413233
OSM 35(LEES CREEK)101.1 | LEES CREEK STREAM REHAB. (NE 30268) | Lackawanna | Carbondale | 2005-06-30 | 2004-01-08 |  | 0 | 52607 |  |  | 47607 |  |  |  |  | 5000
OSM 40(2138)102.1 | CURRYHILL-AVONDALE | Luzerne | Plymouth | 2007-10-12 | 2004-03-24 |  | 136.8 | 3954100.28 | 3695766.27 |  | 258334.01
OSM 40(3213)201.1 | CRANBERRY RIDGE | Luzerne | Hazleton | 2007-01-12 | 2004-02-06 |  | 140 | 2755797.3 |  |  |  | 2755797.3
OSM 40(3725)101.1 | HOLLARS HILL | Luzerne | Hazle |  | 2006-02-14 |  | 141.1 | 2544467 | 2544467
OSM 40(3734)101.1 | WEST SUSCON | Luzerne | Jenkins |  | 2006-01-24 |  | 127.9 | 1663978.55 | 1663978.55
OSM 40(CAN DO)101.1 | CAN DO, INC. INNOVATION (NE 30299) | Luzerne | Hazle | 2005-06-30 | 2004-04-19 |  | 0 | 444615 | 402516 | [6 empty] | 42099
OSM 49(COAL TWP)101.1 | KULPMONT SOUTHWEST (COAL TWP) | Northumberland | Coal |  | 2004-08-04 |  | 0 | 1173926 | 1173927
OSM 54(2024)101.1 | SHARP MOUNTAIN PHASE III (GA) | Schuylkill | Pottsville | 2006-12-31 | 2005-04-01 |  | 0 | 500000 | 500000
OSM 54(2024)102.1 | NORTH SLOPE SHARP MTN PHASE IV (PD50017) | Schuylkill | Pottsville | 2007-12-31 | 2005-11-17 |  | 0 | 422510 | 422509 | [6 empty] | 1 | 3857237
OSM 54(4064)101.1 | PISGAH RIDGE WEST | Schuylkill | Tamaqua | 2005-09-08 | 2002-09-11 |  | 105.3 | 3049740.46 | 37684.75 |  |  | 3012055.71 |  |  |  |  | 1300000
OSM 54(4666)201.1 | LITTLE WOLF CREEK | Schuylkill | East Norwegian |  | 2006-02-10 |  | 268.2 | 10859042.4 | 275000 | [6 empty] | 10584042.4 | 16705917
OSM 56(BOSWELL)101.1 | BOSWELL 2 AMD TREATMENT (SW 30167) | Somerset | Jenner | 2006-06-30 | 2004-01-29 |  | 78 | 258595 | 193595 | [6 empty] | 65000 | 21863154
OSM 63(0046)101.1 | CHARTIERS | Washington | Chartiers | 2007-03-12 | 2004-09-14 |  | 0 | 3593210.8 | 3393210.8 | [5 empty] | 200000
OSM 64,35(YUCCA FLATS)101.1 | LACKAWANNA RIVER/YUCCA FLATS (NE 30634) | Lackawanna | Clifton | 2005-06-30 | 2004-03-15 |  | 0 | 21000 |  |  | 17000 |  |  |  |  | 4000
Future Completions: |  | 77 | Contracts |  |  |  | 2659.75 | 75252591.29 | 46728823.18 | 2198485 | 4203910.13 | 6030181.56 | 500000 | 1366906.69 | 1204546.87 | 12991438.58
Active Design Projects, Future Contract Award Date
AD 0367 | MARY D OPENINGS | Schuylkill | Schuylkill |  |  |  | 0.6
AD 0673 | FALLS CREEK | Bradford | Franklin |  |  |  | 0.2
AD 0675 | HECKSCHERVILLE | Schuylkill | Cass |  |  |  | 0.1
AD 0706 | AD 0706 | Luzerne | Hanover |  |  |  | 0.25
AD 0729 | COLLIERY ROAD | Lackawanna | Dickson City |  |  |  | 0.1
AD 0735 | MAHANOY MOUNTAIN | Northumberland | Zerbe |  |  |  | 0.2
AD 0755 | SWOYERSVILLE NORTH | Luzerne |  |  |  |  | 0
AD 0756 | COURTDALE | Luzerne |  |  |  |  | 0
AD INQ 04-11-362 | PIKE STREET MINE TUNNEL | Lackawanna | Carbondale |  |  |  | 0
AD INQ 05-01-014 | SOMMERS WATER PROBLEM | Schuylkill | Palo Alto |  |  |  | 0
AD INQ 05-01-021 | ZUCHINSKI SUBSIDENCE | Lackawanna | Old Forge |  |  |  | 0
AD PA 1333 | BUTLER | Luzerne | Pittston |  |  |  | 0
AD PA 1610 | NO. 11 VEIN | Northumberland | Coal |  |  |  | 0
AD PA 1782 | TEAGLE | Lackawanna | Scranton |  |  |  | 0.4
AD PA 2004 | AD PA 2004 | Dauphin | Williams |  |  |  | 0.25
AD PA 2152 | STEARNS COLLIERY | Luzerne | Newport |  |  |  | 0
AD PA 2164 | BLACK DESERT | Luzerne | Exeter |  |  |  | 0
AMD 11(0632)101.1 | SALTLICK RUN (MINERAL POINT) | Cambria | Jackson |  |  |  | 3
AMD 11(1110)101.1 | BRUBAKER RUN | Cambria | Dean |  |  |  | 0
AMD 11(2707)101.1 | SOLOMON RUN | Cambria | Stonycreek |  |  |  | 0
AMD 18(0817)101.1 | FRAN CONTRACTING | Clinton | East Keating |  |  | 2006-06-27 | 16
AMD 18(1122)101.1 | ROBBINS HOLLOW | Clinton | Leidy |  |  |  | 0
AMD 24(6134)102.1 | BRANDY CAMP S. (LITTLE TOBY) | Elk | Fox
AMD 26(0429)102.1 | MELCROFT PHASE 2 | Fayette | Saltlick |  |  |  | 30
AMD 26(0429)104.1 | MELCROFT MINE POOL LOWERING | Fayette | Saltlick |  |  | 2006-01-15 | 0
AMD 26(2767)103.1 | ROMNEY NORTH (KALP DISCHARGE)(GA) | Fayette | Saltlick |  | 2005-04-20 |  | 10
AMD 32(2467)101.1 | WEHRUM DISCHARGE | Indiana | Buffington |  |  |  | 0
AMD 42(0420)101.1 | GUM BOOT RUN | McKean | Sergeant |  |  |  | 9
AMD 42(0420)102.1 | GUMBOOT RUN DEEP MINE COMPLEX | McKean |  |  |  |  | 0
AMD 65(2971)101.1 | PINE RUN | Westmoreland | Allegheny |  |  |  | 30
AMD 65(3783)101.1 | HOOVERVILLE SOUTH (NINEVAH) | Westmoreland |  |  |  |  | 550
BD 04-06-387 | BONE MINE DRAINAGE | Allegheny | Wilkins |  |  |  | 0.2
BD 04-09-565 | CRAWFORD MINE DRAINAGE | Allegheny | Penn Hills |  |  |  | 0.2
BD 1744 | CASSIDY | Westmoreland | Irwin |  |  |  | 1
BD 1867-4 | KIM | Lawrence | Neshannock |  |  |  | 0.5
BD 1967 | FRANK | Allegheny | Mount Oliver |  |  |  | 0.5
BD 2012 | DRAVOSBURG | Allegheny | Dravosburg |  |  |  | 0.2
BD 2056 | SCHRADER CREEK | Bradford |  |  |  |  | 0.5
BD 2057 | SCHRADER CREEK | Bradford |  |  |  |  | 0.5
BD 2058 | SCHRADER CREEK | Bradford |  |  |  |  | 0.5
BD 2061 | SCHRADER CREEK | Bradford | Franklin |  |  |  | 0.5
BD 2063 | MANN | Allegheny | South Park |  |  |  | 1
BD 2119-2 | CORDEK | Cambria | South Fork |  |  |  | 0.1
BD 2291-6 | STECKEL/FELOSO | Allegheny | Penn Hills |  |  |  | 0.2
BD 2315-3 | PALLADINO | Allegheny | Plum |  |  |  | 0.2
BD 2429 | HOLLIS | Centre | Rush |  |  |  | 0.2
BD 2449 | HINDS | Mercer | Pine |  |  |  | 0.2
BD 2457-1 | MINE DRAINAGE | Clearfield | Clearfield |  |  |  | 0.2
BD 2466-2 | TRAVIS | Clearfield | Brisbin |  |  |  | 0.2
BD 2494-2 | SOBIEN | Allegheny | Monroeville |  |  |  | 1
BD 2494-3 | SOBIEN | Allegheny | Monroeville |  |  |  | 1
BD 2494-4 | SOBIEN | Allegheny | Monroeville |  |  |  | 1
BD 2529 | HOSTEIN | Allegheny | Wilkins |  |  |  | 0.3
BD 2533-6 | CIRCOLO FEBO | Allegheny | Plum |  |  |  | 0.2
BD 2579 | BLAKE | Armstrong | Kiskiminetas |  |  |  | 0.2
BD 2607 | BD 2607 | Cambria | Susquehanna |  |  |  | 0.1
BD 2666-1 | AME ZION CHURCH MINE DRAINAGE | Allegheny | Pittsburgh (D) |  |  |  | 0
BD 2694 | TORCHIA MINE DRAINAGE | Lawrence | Neshannock |  |  |  | 0.2
BD 2694-01 | TORCHIA MINE DRAINAGE | Lawrence | Neshannock |  |  |  | 0.2
BD 2697-1 | KASCAK MINE DRAINAGE | Allegheny | Kennedy |  |  |  | 0.2
BD 2701 | PURDY MINE DRAINAGE | Allegheny | Wilkins |  |  |  | 0.2
BD 2702 | LORELLI MINE DRAINAGE | Jefferson | McCalmont |  |  |  | 0.2
BD 2707-1 | BD 2707-1 | Clearfield | Huston |  |  |  | 0
BD 2712 | ABANDONED SURFACE MINE | Clearfield | Bigler |  |  |  | 3
BD 2715 | BONE MINE DRAINAGE | Allegheny | Wilkins |  |  |  | 0.2
BD 2718 | GORNATTI | Elk | Fox |  |  |  | 0
BD 2721 | KITCHEN MINE DRAINAGE | Clarion | Piney |  |  |  | 0.2
BD 2722 | MAMAU MINE SUBSIDENCE | Indiana | Grant |  |  |  | 0
BD 2723 | TUCKER | Allegheny | Penn Hills |  |  |  | 0
BD 2725 | FIFTH AVENUE TR 300 | Clearfield | Woodward |  |  |  | 0
BD 2726 | MINE DRAINAGE | Clearfield | Decatur |  |  |  | 0
BD 2727 | LOUIS GRAHAM | Clearfield | Bradford |  |  |  | 0
BD 2728 | YAVORSKY | Clearfield | Gulich |  |  |  | 0
BD 2729 | FESS SUBSIDENCE | Indiana | Center |  |  |  | 0
BD 2730 | FELTON SUBSIDENCE | Westmoreland | Unity |  |  |  | 0
BD 2731 | KLUCHUROSKY MINE DRAINAGE | Indiana | Green |  |  |  | 0
BD 2732 | DAWSON MINE SUBSIDENCE | Westmoreland | Unity |  |  |  | 0
BD 2733 | MCGHEE MINE DRAINAGE | Allegheny | Churchill |  |  |  | 0
BD 2734 | MINE DRAINAGE | Centre | Snow Shoe |  |  |  | 0.2
BD 2736 | HUBNER MINE DRAINAGE | Allegheny | Plum |  |  |  | 0
BD 2738 | MELANDER DRAINAGE | Clearfield | Bigler |  |  |  | 0
BD 2741 | RISHER MINE | Allegheny | West Mifflin |  |  |  | 0
BD 2744 | PATTERSON MINE DRAINAGE | Allegheny | Penn Hills |  |  |  | 0
BD 2745 | MINE DRAINAGE | Allegheny | Carnegie |  |  |  | 0
BD 2757-1 | CRAWFORD | Allegheny | Pittsburgh (D) |  |  |  | 0.3
BD 2759 | KNAPIK MINE SUBSIDENCE | Cambria | Northern Cambria |  |  |  | 0
BD 2760 | TOURNAY MINE DRAINAGE | Allegheny | McDonald |  |  |  | 0
BD 2762 | TOTH MINE DRAINAGE | Allegheny | Munhall |  |  |  | 0.2
BD 2770 | PANGBURN HOLLOW - RAMSEY PROPERTY | Allegheny | Forward |  |  |  | 0
BF 392-102.1 | GLENN COAL CO. | Jefferson | Oliver |  |  |  | 0
BF 396-102.1 | THOMAS A. FELLO | Indiana | Conemaugh |  |  |  | 0
BF 405-101.1 | RUSSELL JOKI (I) (CONSULT. DESIGN) | Washington | Union |  |  |  | 37
BF 445-102.1 | GLACIAL MINERALS, INC. (STRATTANVILLE) | Clarion | Clarion |  |  | 2006-04-25 | 15
BF 445-103.1 | GLACIAL MINERALS, INC. (REED) | Clarion | Clarion |  |  | 2006-04-25 | 8
BF 461-101.1 | CAMBRIA MILLS COMPANY | Clearfield | Beccaria |  |  |  | 0
BF 465-101.1 | PENGROVE COAL COMPANY(EAKIN) | Venango | Clinton |  |  | 2006-12-30 | 23.5
BF 468 | PENGROVE COAL COMPANY(RUTH) | Butler | Venango |  |  |  | 0
BF 483-101.1 | RONDELL-CORREAL (NEWMYER RUN) PHASE I | Fayette | Saltlick |  |  | 2006-07-25 | 47
BF 484-101.1 | BRYAR CONSTRUCTION | Westmoreland | Hempfield |  |  |  | 0
BF 487-101.1 | HAMILTON BROTHERS COAL, INC. | Clearfield | Beccaria |  |  | 2005-11-30 | 33
BF 491-101.1 | HAMILTON BROTHERS COAL, INC. | Clearfield | Beccaria |  |  |  | 82
BF 500-101.1 | PENGROVE COAL COMPANY(MARTIN BELL) | Venango | Clinton |  |  |  | 0
BF 508-101.1 | EBONY COAL COMPANY | Westmoreland | Penn |  |  | 2006-05-30 | 26
BF 516-101.1 | GLACIAL MINERALS, INC. | Venango | Richland |  |  |  | 0
BF 517-101.1 | GLACIAL MINERALS, INC. | Clarion | Porter |  |  |  | 0
BF 518-101.1 | GLACIAL MINERALS, INC. | Clarion | Richland |  |  |  | 0
BF 519-101.1 | GLACIAL MINERALS, INC. | Clarion | Monroe |  |  |  | 0
BF 520-101.1 | BENJAMIN COAL CO. | Clearfield | Brady |  |  |  | 0
CRF 002-101.1 | WEST NEWTON COAL LOGISTICS CO. | Westmoreland | Rostraver
DMF 002-104.1 | DARMAC ASSOCIATES CORP. | Butler | Oakland |  |  |  | 0
DMF 013-139.1 | DOVERSPIKE BROTHERS COAL, CO.-DORA #6 | Jefferson | Perry |  |  | 2006-08-30 | 1
DMF 013-140.1 | DOVERSPIKE BROTHERS COAL, CO.-DORA #6 | Jefferson | Perry |  |  | 2006-07-25 | 8
NCF 006-101.1 | BUCKEYE WRECKING & TRANSFER, INC. | Westmoreland | Vandergrift |  |  | 2006-08-29 | 7
OSM 02(0275)101.1 | KARAFFA MINE DRAINAGE | Allegheny | Port Vue |  |  |  | 0
OSM 02(2602)101.1 | LG.MINE FIRE (TEPE PUMP STA.) | Allegheny | Jefferson Hills |  |  |  | 100
OSM 03(1574)101.1 | SLABTOWN NORTHWEST | Armstrong | Boggs |  |  | 2006-06-02 | 14
OSM 03(2973)101.1 | TIDAL NORTHEAST | Armstrong | Madison |  |  |  | 0
OSM 03(3359)101.1 | GOHEENVILLE N.E. (MAHONING LAKE) | Armstrong | Wayne |  |  |  | 0
OSM 03(3498)101.1 | CHARLESTOWN SOUTHWEST | Armstrong | Redbank |  |  |  | 0
OSM 04(6279)101.1 | MISKITA LAKE FAR SOUTHWEST | Beaver | South Beaver |  |  |  | 0
OSM 10(0674)101.1 | SLIPPERY ROCK SOUTH | Butler | Slippery Rock |  |  | 2006-02-28 | 21
OSM 10(0752)101.1 | SHERWIN NORTH | Butler | Clay |  |  |  | 0
OSM 10(0760)101.1 | FINDLAY RUN WEST | Butler | Cherry |  |  | 2006-02-15 | 20
OSM 10(2922)101.1 | COALTOWN SOUTH | Butler | Cherry |  |  |  | 0
OSM 10(3917)101.1 | DENNYS MILLS NORTH | Butler | Winfield |  |  | 2006-04-15 | 9
OSM 10(4330)101.1 | VOGLEYVILLE | Butler | Summit |  |  |  | 40
OSM 10(6493)101.1 | WEST LIBERTY EAST #3 | Butler | West Liberty |  |  | 2007-02-28 | 5
OSM 10(6592)101.1 | CHERRY VALLEY SOUTH | Butler | Cherry Valley |  |  |  | 0
OSM 10(7000)101.1 | EAU CLAIRE SOUTHWEST | Butler | Allegheny |  |  |  | 4
OSM 10(7138)101.1 | WHISKERVILLE WEST | Butler | Washington |  |  |  | 0
OSM 11(2810)101.1 | SLATE LICK RUN EAST | Cambria | White |  |  |  | 0
OSM 11(4789)101.1 | WYEROUGH RUN NORTH | Cambria | Chest |  |  |  | 32
OSM 13(4653)101.1 | NESQUEHONING SOUTHWEST | Carbon | Nesquehoning |  |  | 2006-04-01 | 19.6
OSM 13,40(3204)101.1 | BEAVER BROOK | Carbon | Banks |  |  |  | 0
OSM 14(0883)101.1 | ORVISTON | Centre | Curtin |  |  | 2007-05-30 | 17
OSM 16(0992)101.1 | SOUTH OF SHAMBURG | Clarion | Piney |  |  | 2006-02-28 | 14
OSM 16(2826)101.1 | FAIRMOUNT CITY (CONSULT.DESIGNED) | Clarion | Redbank |  |  |  | 0
OSM 16(3410)101.1 | RIMERSBURG EAST | Clarion | Toby |  |  |  | 23
OSM 16(6049)101.1 | ST. NICHOLAS CEMETERY EAST | Clarion | Limestone |  |  | 2006-11-28 | 3
OSM 16(6204)101.1 | UNKNOWN MAPLE GROVE | Clarion | Madison |  |  | 2006-07-30 | 82
OSM 16(6700)101.1 | CLARION LIMESTONE HS NW | Clarion | Clarion |  |  | 2006-12-19 | 33
OSM 17(0115)101.1 | SANDY CREEK #1 | Clearfield | Covington |  |  | 2006-09-26 | 22
OSM 17(0620)101.1 | SALEM CHURCH SOUTH | Clearfield | Knox |  |  |  | 45
OSM 17(1395)101.1 | GRAMPIAN | Clearfield | Penn |  |  | 2006-05-30 | 34
OSM 17(1946)101.1 | DRANE | Clearfield | Decatur |  |  |  | 0
OSM 17(2998)101.1 | NEEDFUL SOUTH NO. 1 | Clearfield | Bradford |  |  |  | 62
OSM 17(3992)101.1 | STUMPTOWN NORTH | Clearfield | Decatur |  |  |  | 0
OSM 17(4454)102.1 | BCI WATERLINE AREA A (GA) | Clearfield | Beccaria |  |  |  | 0
OSM 17(4537)101.1 | ALBERT LANDING FIELD SOUTH | Clearfield | Morris |  |  |  | 22
OSM 17(4544,4545)101.1 | ALDER RUN WEST | Clearfield | Morris |  |  |  | 92
OSM 17(6801)101.1 | GRASSFLAT NORTHWEST | Clearfield | Cooper |  |  | 2006-09-30 | 203
OSM 17(7004)102.1 | OWENS CEMETERY | Clearfield | Clearfield |  |  |  | 1.5
OSM 17(7086)101.1 | BLUEBALL EAST | Clearfield | Morris |  |  | 2006-11-30 | 25
OSM 17(7180)101.1 | GOSHEN SOUTH SITE | Clearfield | Goshen |  |  | 2006-08-30 | 6
OSM 19(4032)101.1 | ARISTES EAST | Columbia | Conyngham |  |  |  | 0
OSM 24(0521)101.1 | CALEDONIA NORTHWEST | Elk | Jay |  |  |  | 20
OSM 24(0525)101.1 | GRAY HILL | Elk | Jay |  |  | 2006-06-02 | 85
OSM 24(3888)101.1 | DARK HOLLOW | Elk | Benezette |  |  |  | 0
OSM 24(3890)101.1 | DENTS RUN | Elk | Benezette |  |  |  | 0
OSM 24(3897)101.1 | PORCUPINE HOLLOW I | Elk | Benezette |  |  |  | 0
OSM 24(3898)101.1 | PORCUPINE HOLLOW II | Elk | Benezette |  |  | 2006-04-15 | 49
OSM 26(0149)101.1 | LINDA WEAVER SUBSIDENCE | Fayette | Upper Tyrone |  |  |  | 0
OSM 26(1821)101.1 | NAOMI EAST (CONSULT.DESIGNED) | Fayette | Washington |  |  |  | 0
OSM 26(2718)104.1 | PERCY MINE FIRE | Fayette | North Union |  |  |  | 0
OSM 26(4715)101.1 | ROGERS MILL SOUTH (KOOSER ROAD WATER LINE) | Fayette | Springfield |  |  |  | 0
OSM 33(1389)101.1 | HARVEY'S RUN NORTH | Jefferson | Washington |  |  |  | 15
OSM 35(1524)102.1 | GRASSY ISLAND CREEK | Lackawanna | Archbald |  |  | 2005-12-31 | 116.5
OSM 35(2078)102.1 | EDDY CREEK (SEE 101.1 - COMBINED) | Lackawanna | Olyphant |  |  | 2006-04-30 | 20
OSM 35(2179)103.1 | TAYLOR SOUTH MAIN | Lackawanna | Taylor |  |  |  | 0
OSM 35(2185)102.1 | KEYSER AVENUE/SCRANTON | Lackawanna | Scranton |  |  | 2004-08-30 | 2
OSM 35(3735)102.1 | GREENWOOD | Lackawanna | Moosic |  |  | 2006-05-31 | 20.9
OSM 35(3738)102.1 | NORTH GOLF COURSE | Lackawanna | Taylor |  |  |  | 0
OSM 35(3742)201.1 | GRASSY ISLAND | Lackawanna | Olyphant |  |  | 2006-03-01 | 61.7
OSM 35(4190)101.1 | INTERCHANGE 56 SOUTH | Lackawanna | Scranton |  |  |  | 25
OSM 37(4481)101.1 | DUCKRUN EAST | Lawrence | Wayne |  |  | 2006-10-30 | 6
OSM 37(4489)101.1 | MARTIN ROAD | Lawrence | Slippery Rock |  |  | 2007-01-30 | 85
OSM 40(0493)101.1 | HOLLARS HILL SOUTH | Luzerne | Hazle |  |  | 2006-08-30 | 239.8
OSM 40(1365)101.1 | HAZLETON S.C. WEST | Luzerne | Hazleton |  |  | 2004-12-31 | 77
OSM 40(1372,1374)101.1 | HUMBOLDT S.W. | Luzerne | Hazle |  |  | 2006-06-30 | 111.8
OSM 40(1381)101.1 | FREELAND SOUTH | Luzerne | Hazle |  |  |  | 15
OSM 40(1859)101.1 | LAUREL RUN CREEK (PARSONS) | Luzerne | Wilkes-Barre |  |  | 2004-09-30 | 1
OSM 40(2132)102.1 | PINE CREEK RESERVOIR | Luzerne | Wilkes-Barre |  |  | 2004-12-31 | 3
OSM 40(2165)101.1 | HILLDALE | Luzerne | Plains |  |  | 2005-12-31 | 32
OSM 40(3044)101.1 | FERN GLEN | Luzerne |  |  |  | 2006-08-31 | 100
OSM 40(3217)101.1 | DRIFTON | Luzerne | Hazle |  |  | 2006-03-30 | 15
OSM 43(0116)101.1 | BLACKTOWN | Mercer | Springfield |  |  |  | 29
OSM 43(4284)101.1 | NESBIT CORNERS EAST | Mercer | Worth |  |  | 2006-01-01 | 23
OSM 54(1002,4044)101.1 | GIRARDVILLE EAST | Schuylkill | Girardville |  |  | 2005-12-31 | 0
OSM 54(2011,3014)102.1 | , POPLAR RUN | Schuylkill | Tremont
OSM 54(2025)103.1 | PALO ALTO NORTH | Schuylkill | Palo Alto |  |  | 2006-01-15 | 0
OSM 54(2029)101.1 | DONALDSON | Schuylkill |  |  |  | 2004-12-31 | 26
OSM 54(3042)102.1 | ONEIDA WEST | Schuylkill | North Union |  |  | 2005-12-31 | 351
OSM 54(3046)101.1 | GREENE MTN. S. | Schuylkill | East Union |  |  | 2005-06-30 | 113
OSM 54(3630)101.1 | PINE HILL NORTH | Schuylkill | Cass |  |  | 2005-03-01 | 250
OSM 54(3633)103.1 | MOUNT PLEASANT | Schuylkill | Foster |  |  | 2006-02-28 | 22.7
OSM 54(3649)102.1 | NEWTOWN SOUTH 2 | Schuylkill | Reilly |  |  | 2005-06-30 | 50
OSM 54(3703)104.1 | NORTH DONALDSON | Schuylkill | Frailey |  |  | 2006-04-30 | 25
OSM 54(3727)101.1 | NORTH SHEPPTON | Schuylkill | East Union |  |  | 2007-12-31 | 120
OSM 54(4208)102.1 | ROBINSON | Schuylkill | Frailey |  |  |  | 1.5
OSM 56(0783)101.1 | BROTHERTON NORTH | Somerset |  |  |  |  | 0
OSM 56(2517)101.1 | RAILROAD STREET | Somerset | Paint |  |  |  | 7
OSM 61(2906)101.1 | WOODS CORNERS | Venango | Irwin |  |  | 2006-05-30 | 20
OSM 61(6942)101.1 | EMLENTON WEST | Venango | Scrubgrass |  |  | 2006-02-28 | 32
OSM PA (AMR-05)CANDO GREEN MTN TUNNEL | GREEN MOUNTAIN TUNNEL WATER TREATMENT PLANT | Schuylkill | East Union |  |  |  | 0
OSM PA(AMD-04)LUP OPTIMIZATION | LIMESTONE UPFLOW POND OPTIMIZATION | Clarion |  |  |  | 2006-03-01 | 0
OSM PA(AMD-04)MANGANESE | MANGANESE RESOURCE RECOVERY | Butler |  |  |  | 2006-03-15 | 0
OSM PA(AMD-04)PHOSPHOROUS | PHOSPHOROUS REMOVAL USING AIS SLUDGE | Westmoreland |  |  |  | 2006-03-15 | 0
OSM PA(AMD-04)POWDERED METALS | POWDERED METALS FROM IRON OXIDE SLUDGE | Elk |  |  |  | 2006-03-01 | 0
Future Awards: |  | 208 | Contracts |  |  |  | 4073.6 | 70491880.55 | 6646803.99 | 814050 | 3219091.4 | 0 | 0 | 1253383.35 | 32400.22 | 5147532.09